## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. 2. The worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses:
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: | Beneficary Member State (Dropdown Menu):
2023 | Poland | should we already add the new bMS?

## Annual Report
General information | [9 empty] | Financial information | [7 empty] | Contribution to Green Deal Objectives | [7 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Implementation status | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery | Confirmation of co-financing from private sources (for non-priority investments) | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [7 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: XX/YY/20ZZ] | Identified or expected delays in implementation | For investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[18 empty] | Energy saved in MWh |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment)
[18 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2021-1 PL 0-004 | MF 2021-1 PL 0-004 | Renovation with a guarantee of savings | Priority | Scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Polczynskie Przedsiebiorstwo Komunalne sp. z o.o. | Poland | 123000000 | 100000000 | 25000000 | 25000000 | 284555 | 33502 | n/a | n/a | 174 | 1917 | 226 | 2489 | n/a | n/a | 1257 | 114 | Yes, 2022 | calls for proposals: 1 project proposals: 9 preliminary applications / 2 applications for funding agreements concluded: 1 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | n/a | call for proposals/ application selection criteria / beneficiary statement
2 | MF 2021-1 PL 0-003 | MF 2022-2 PL 0-001 | Smart energy infrastructure | Priority | Large-scale scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Stoen Operator; - Energa Operator; - PDE Dystrybucja | Poland | 273000000 | 222000000 | 222000000 | 222000000 | 45832328 | 13746901 | n/a | n/a | n/a | n/a | 86436 | 1037233 | n/a | n/a | 530 | 44 | Yes, 2022 | calls for proposals: 2 project proposals: 6 agreements concluded: 3 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Elektroenergetyka inteligentna infrastruktura energetyczna - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
3 | MF 2021-1 PL 0-006 | MF 2021-1 PL 0-006 MF 2023-2 PL 0-003 | Development of the power grid for future electric car charging stations | Priority | Large-scale scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - ENEA Operator; - Stoen Operator; - Energa Operator; - PGE Dystrybucja | Poland | 455000000 | 370000000 | 222000000 | 127000000 | 45325369 | 6048589 | n/a | n/a | n/a | n/a | 8329 | 333160 | n/a | n/a | 5442 | 136 | Yes, 2022 | calls for proposals: 1 project proposals: 7 agreements concluded: 4 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Rozwój infrastruktury elektroenergetycznej na potrzeby rozwoju stacji ładowania pojazdów elektrycznych - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
4 | MF 2021-2 PL 0-002 | MF 2023-2 PL 0-002 | Cogeneration for Energy and Industry | Priority | Large-scale scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Velvet Care Sp. z o.o. | Poland | 546000000 | 444000000 | 444000000 | 69140000 | 7069921 | 444444 | n/a | n/a | 75993.89 | 1519877.8 | 68924 | 1378480 | n/a | n/a | 102.58 | 5.13 | Yes, 2022 | calls for proposals: 1 project proposals: 7 agreements concluded: 1 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Kogeneracja dla Energetyki i Przemysłu - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
5 | MF 2023-2 PL 0-001 | MF 2023-2 PL 0-001 | Cogeneration for Energy and Industry - sectors in energy trasition | Priority | Large-scale scheme | Tender ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | The beneficiaries of the program are Entrepreneurs within the meaning of the Act of March 6, 2018, Entrepreneurs' Law, conducting business activities. | Poland | 411000000 | 334000000 | 334000000 | 44570000 | 0 | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO | calls for proposals: to be announced 2nd Q 2024 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Kogeneracja dla Energetyki i Przemysłu - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
6 | MF 2021-2 PL 0-003 | MF 2021-2 PL 0-003 | Cogeneration For District heating | Priority | Large-scale scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Miejska Energetyka Cieplna w Koszalinie sp. z o.o.; - Miejskie Przedsiebiorstwo Energetyki Cieplnej sp. z o.o. | Poland | 820000000 | 666660000 | 666660000 | 66600000 | 28977778 | 2222 | n/a | n/a | 406703 | 6507247 | 61343 | 981493 | n/a | n/a | 472 | 30 | Yes, 2022 | calls for proposals: 1 project proposals: 26 agreements concluded: 4 | n/a | The managing authority started the process of signing contracts on December 8, 2023 by signing the Vice-President of the Management Board. The contract signing procedure ended on December 8, 2023, and the payment was made on December 8, 2023. | n/a | to be specified (due to ongoing new EU ETS provisions process) | Kogeneracja dla Ciepłownictwa - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
7 | MF 2023-1 PL 0-002 | MF 2023-1 PL 0-002 | Cogeneration For District heating - part II | Priority | Scheme | Tender ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Przedsiebiorstwo Energetyki Cieplnej w Suwalkach sp. z o.o. | Poland | 27000000 | 22220000 | 22220000 | 2220000 | 23383329 | 0 | n/a | n/a | 39309 | 786180 | 16547 | 330940 | n/a | n/a | 1413 | 71 | NO | calls for proposals: 1 project proposals: 8 agreements concluded: 2 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | n/a | call for proposals/ application selection criteria / beneficiary statement
8 | MF 2021-2 PL 0-005 | MF 2021-2 PL 0-005 | Digitisation of heating networks | Priority | Large-scale scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Okregowe Przedsiebiorstwo Energetyki Cieplnej w Pulawach sp. z o.o. | Poland | 137000000 | 111110000 | 111110000 | 33300000 | 1666067 | 133333 | n/a | n/a | 10596 | 52980 | 962 | 4810 | n/a | n/a | 1732 | 346 | Yes, 2022 | calls for proposals: 1 project proposals: 13 agreements concluded: 2 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Digitalizacja Sieci Ciepłowniczych - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
9 | MF 2021-2 PL 0-004 | MF 2021-2 PL 0-004 MF 2022-1 PL 0-001 MF 2022-1 PL 0-007 MF 2023-1 PL 0-001 | The use of alternative fuels for energy purposes | Priority | Large-scale scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: https://www.gov.pl/web/funduszmodernizacyjny/zawarte-umowy | Poland | 1884000000 | 1532000000 | 1332000000 | 310800000 | 567082284 | 883292 | n/a | n/a | 267939 | 7184131 | 322975 | 8214256 | n/a | n/a | 1758 | 69 | Yes, 2022 | calls for proposals: 1 project proposals: 78 agreements concluded: 26 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Wykorzystanie paliw alternatywnych na cele energetyczne - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
10 | MF 2021-2 PL 0-001 | MF 2021-2 PL 0-001 | Support for the use of storages and other devices for network stabilization - a scheme for DSOs | Priority | Large-scale scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - PGE Dystrybucja | Poland | 273000000 | 222220000 | 222220000 | 44440000 | 9589333 | 26667 | n/a | n/a | n/a | n/a | 2132 | 42639 | n/a | n/a | 4498 | 225 | Yes, 2022 | calls for proposals: 1 project proposals: 1 agreements concluded: 1 | n/a | The managing authority started the process of signing contracts on December 7, 2023 by signing the Vice-President of the Management Board. The contract signing procedure ended on December 7, 2023, and the payment was made on December 13, 2023. | n/a | to be specified (due to ongoing new EU ETS provisions process) | Wsparcie wykorzystania magazynów oraz innych urządzeń na cele stabilizacji sieci - program dla Operatorów Sieci Dystrybucyjnych - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
11 | MF 2022-1 PL 0-004 | MF 2022-1 PL 0-004 | Energy-intensive Industry – RES | Priority | Large-scale scheme | Tender ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | The beneficiaries of the program are the entrepreneurs within the meaning of the Act of March 6, 2018, Entrepreneurs' Law, who have a legal title to an installation covered by the greenhouse gas emission allowances trading system within the meaning of the Act of June 12, 2015. | Poland | 213000000 | 173000000 | 144000000 | 11110000 | 0 | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes, 2022 | calls for proposals: 2 project proposals: 3 agreements concluded: 0 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Przemysł energochłonny - OZE - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
12 | MF 2022-1 PL 0-003 | MF 2022-1 PL 0-003 | Energy-intensive industry - improving energy efficiency | Priority | Scheme | Tender ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Südzucker Polska Spółka Akcyjna | Poland | 115000000 | 93350000 | 77790000 | 11110000 | 28444444 | 0 | n/a | n/a | n/a | n/a | 30157 | 603137 | n/a | n/a | 943 | 47 | Yes, 2022 | calls for proposals: 1 project proposals: 1 agreements concluded: 1 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | n/a | call for proposals/ application selection criteria / beneficiary statement
13 | MF 2022-2 PL 0-003 | MF 2022-2 PL 0-003 | Energy for Rural Areas | Priority | Large-scale scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: https://www.gov.pl/web/funduszmodernizacyjny/zawarte-umowy | Poland | 318000000 | 258200000 | 209900000 | 20990000 | 32312377 | 3713229 | n/a | n/a | n/a | n/a | 32006 | 640110 | 3.3 | 3.3 | 1010 | 50 | Yes, 2022 | calls for proposals: 1 project proposals: 216 agreements concluded: 30 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Energia dla wsi - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
14 | MF 2022-2 PL 0-002 | MF 2022-2 PL 0-002 | Cogeneration for counties | Priority | Large-scale scheme | Tender ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Entrepreneurs within the meaning of the Act of March 6, 2018, Entrepreneurs' Law, conducting business activity in the field of heat generation or heat and electricity production, implementing a project as part of the heating system, with the ordered thermal power, as at the date of submitting the application, below 50 MW. | Poland | 273000000 | 222220000 | 222220000 | 22200000 | 0 | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes, 2022 | calls for proposals: 1 project proposals: 31 agreements concluded: 0 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Kogeneracja powiatowa - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
15 | MF 2022-2 PL 0-004 | MF 2022-2 PL 0-004 | Development of cogeneration based on municipal biogas | Priority | Large-scale scheme | Tender ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Miedzygminny Kompleks Unieszkodliwiania Odpadow ProNatura sp. z o.o. | Poland | 410000000 | 333000000 | 333000000 | 44440000 | 28034529 | 0 | n/a | n/a | 8837 | 114881 | 15438 | 200694 | 1.9 | 1.9 | 1816 | 140 | Yes, 2022 | calls for proposals: 1 project proposals: 11 agreements concluded: 2 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Rozwój kogeneracji w oparciu o biogaz komunalny - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
16 | MF 2022-2 PL 1-001 | MF 2022-2 PL 1-001 | RES - heat sources for district heating | Non-priority | Large-scale scheme | Tender ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Program beneficiaries: entrepreneurs within the meaning of the Act of March 6, 2018, Entrepreneurs' Law, conducting business activity in the field of heat generation or cogeneration of heat and electricity. | Poland | 781000000 | 635000000 | 444440000 | 22222222 | 0 | 0 | n/a | n/a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes, 2022 | calls for proposals: 1 project proposals: 0 agreements concluded: 0 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | OZE - źródło ciepła dla ciepłownictwa - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement
17 | MF 2021-2 PL 1-001 | MF 2021-2 PL 1-001 MF 2022-2 PL 1-002 | My Heating | Non-priority | Large-scale scheme | Construction ongoing | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Programy Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | The final recipients of the aid will be natural persons. The program is addressed to owners or co-owners (end recipients) of new single-family buildings. Beneficiaries that have been awarded support: https://mojecieplo.gov.pl/wyniki-naboru/ | Poland | 547000000 | 444400000 | 133330000 | 133333333 | 27134700 | 27134700 | n/a | YES (applicant's statement and documents confirming payments) | 158113 | 3162252 | 15541 | 310829 | 121 | n/a | 1746 | 87 | Yes, 2022 | calls for proposals: 1 project proposals: 21 586 agreements concluded: 14 438 | n/a | n/a | n/a | to be specified (due to ongoing new EU ETS provisions process) | Moje Ciepło - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | call for proposals/ application selection criteria / beneficiary statement

## Overview Planned Investments
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment | 1.4 Summary description of the investment | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1 | Construction of home wind turbines with electricity storage facilities (program for prosumers) | NFWMEP | Poland | 444444444.4444 | The aim of the program is to increase the production of electricity from wind turbines and/or to increase the self-consumption of the generated electricity through its storage (electricity storage facilities). | to be specified (generally none) | 444444444.4444 | The investment proposal is compatible with the polish National Energy and Climate Plan for the years 2021-2030, especially with regard to five main dimensions of the Energy Union: - decarbonisation - energy efficiency - energy security - internal energy market - research, innovation and competitiveness. | n/a | 2024.01.29 - 2024.02.05 | online (via website) | representatives of entrepreneurs, social organizations, members of scientific institutions, representatives of the professional heat and power industry, local government officials, natural persons | comments (over 100 suggestions) were received from several dozen entities from various industries | Podsumowanie_I_konsultacji-_Program_Moja_elektrownia_wiatrowa.pdf
2 | The use of hydrogen in the transport sector | NFWMEP | Poland | 666666666.6667 | The aim of the Program is to support the hydrogen-based transport sector. | to be specified | 666666666.6667 | The investment proposal is compatible with the polish National Energy and Climate Plan for the years 2021-2030, especially with regard to five main dimensions of the Energy Union: - decarbonisation - energy efficiency - energy security - internal energy market - research, innovation and competitiveness. | n/a | 2024.04.02 - 19 | online (via website) | representatives of entrepreneurs, social organizations, members of scientific institutions, representatives of the professional heat and power industry, local government officials, natural persons | comments (over 100 suggestions) were received from several dozen entities from various industries | consultations ended on April 19 - the answer is being prepared - it will be immediately published on the website
3 | Support for the use of storagefacilities and other devices for network stabilization purposes (program for entrepreneurs). | NFWMEP | Poland | 555555555.5556 | The aim of the program is to improve the stability of the NPS operation and the country's energy security by supporting the construction of independent electricity storage facilities with a capacity of not less than 50 MW and a capacity of not less than 200 MWh, connected to the highest voltage distribution or transmission grid. | to be specified | 555555555.5556 | The investment proposal is compatible with the polish National Energy and Climate Plan for the years 2021-2030, especially with regard to five main dimensions of the Energy Union: - decarbonisation - energy efficiency - energy security - internal energy market - research, innovation and competitiveness. | n/a | 2024.04.02 - 19 | online (via website) | representatives of entrepreneurs, social organizations, members of scientific institutions, representatives of the professional heat and power industry, local government officials, natural persons | comments (over 100 suggestions) were received from several dozen entities from various industries | consultations ended on April 19 - the answer is being prepared - it will be immediately published on the website
4 | Support for projects with IPCEI status | NFWMEP | Poland | to be specified | The aim of the program is to provide financing for the full implementation of IPCEI hydrogen projects beyond the horizon of availability of funds of the National Recovery Plan, limited to 2026. | In accordance with the individual EC notification decision for the IPCEI project | to be specified | The investment proposal is compatible with the polish National Energy and Climate Plan for the years 2021-2030, especially with regard to five main dimensions of the Energy Union: - decarbonisation - energy efficiency - energy security - internal energy market - research, innovation and competitiveness. | n/a | 2024.04.02 - 19 | online (via website) | representatives of entrepreneurs, social organizations, members of scientific institutions, representatives of the professional heat and power industry, local government officials, natural persons | comments (over 100 suggestions) were received from several dozen entities from various industries | consultations ended on April 19 - the answer is being prepared - it will be immediately published on the website
5 | Energy-efficient use of methane in the mining sector | NFWMEP | Poland | 444444444.4444 | The aim of the Program is to support the mining sector in increasing energy efficiency through the use of methane, i.e. the use of cheap, ecological energy raw material in the methane removal process by capturing and removing methane from raw material deposits. Reducing methane emissions, in addition to ensuring safety, makes it possible to produce heat or electricity from the gas accompanying mining processes. Additionally, large methane resources in raw material deposits and their economic use for energy purposes are a great economic and ecological opportunity. | to be specified | 444444444.4444 | The investment proposal is compatible with the polish National Energy and Climate Plan for the years 2021-2030, especially with regard to five main dimensions of the Energy Union: - decarbonisation - energy efficiency - energy security - internal energy market - research, innovation and competitiveness. | n/a | 2024.04.02 - 19 | online (via website) | representatives of entrepreneurs, social organizations, members of scientific institutions, representatives of the professional heat and power industry, local government officials, natural persons | comments (over 100 suggestions) were received from several dozen entities from various industries | consultations ended on April 19 - the answer is being prepared - it will be immediately published on the website
6 | Construction, expansion and modernization of power transmission networks | NFWMEP | Poland | to be specified | The aim of the Program is to support the construction, expansion and modernization of transmission networks/power stations, which will contribute to increasing the possibilities of integrating renewable energy sources and reducing the level of energy losses in transmission. | to be specified | to be specified | The investment proposal is compatible with the polish National Energy and Climate Plan for the years 2021-2030, especially with regard to five main dimensions of the Energy Union: - decarbonisation - energy efficiency - energy security - internal energy market - research, innovation and competitiveness. | n/a | 2024.04.02 - 19 | online (via website) | representatives of entrepreneurs, social organizations, members of scientific institutions, representatives of the professional heat and power industry, local government officials, natural persons | comments (over 100 suggestions) were received from several dozen entities from various industries | consultations ended on April 19 - the answer is being prepared - it will be immediately published on the website
7
8
9
10
11
XX

## Dropdown Menu (hidden)
bMS | Year
Column1 | Column2
- | 2021
Bulgaria | 2022
Czechia | 2023
Estonia | 2024
Greece | 2025
Croatia | 2026
Latvia | 2027
Lithuania | 2028
Hungary | 2029
Poland | 2030
Portugal
Romania
Slovenia
Slovakia