## Introduction
Modernisation Fund Annual Report Template
Introduction to the Excel-tool "Modernisation_Fund_Annual_Report_Template.xlsx"
The "Modernisation_Fund_Annual_Report_Template.xlsx" is a resource drafted by the European Commission, Directorate-General for Climate Action, designed to streamline the data submission process for the annual reports of beneficiary Member States.
Article 13 of the Commission Implementing Regulation (EU) 2020/1001 provides that beneficiary Member States shall monitor the implementation of investments financed from the Modernisation Fund and submit to the Commission their annual report for the preceding year containing information specified in Annex II of the Implementing Regulation (EU) 2020/1001. The annual report shall be be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview. The relevant stakeholders should be consulted on the draft overview of the planned investments.
This template for annual reports provides 3 worksheets: 1. The worksheet labeled 'Introduction' offers an explanation of the template. It contains a dropdown menu that allows you to configure the template according to the beneficary member state and the corresponding year of the annual report. It also includes an overview of the approved investments.
2. In the worksheet named 'Annual Report' you will find a request for information according to Annex II of the Implementing Regulation (EU) 2020/1001. The requested information is categorised into 6 categories. Please follow the instructions to fill this in.
3. The worksheet titled 'Overview Planned Investments' requires supplementary details according to Annex III of the Implementing Regulation (EU) 2020/1001 and 'shall be accompanied by an overview of the investments in respect of which the beneficiary Member State intends to submit investment proposals in the next two calendar years, with an outlook until 2030, as well as by updated information on investments covered by any previous overview.'
OVERVIEW OF APPROVED INVESTMENTS
|  |  | Investments supported (ongoing+completed+partially discontinued+fully discontinued) | Ongoing investments | Completed investments (or entered into operations) | Partially discontinued investments | Discontinued investments
Priority investments | Number |  | 27 | 27 | 0 | 0 | 0
| Total confirmed/recommended support from the Modernisation Fund for the investment in EUR |  | 4154160000 | 4154160000 | 0 | 0 | 0
Non-priority investments | Number |  | 3 | 3 | 0 | 0 | 0
| Total confirmed/recommended support from the Modernisation Fund for the investment in EUR |  | 229355555 | 229355555 | 0 | 0 | 0
We welcome any improvement suggestions for the tool from the beneficiary Member States. Please feel free to contact via the following email addresses: |  |  |  | INSTRUCTIONS: In order to guarantee that all beneficiary Member States provide comparable reporting, the following methodological instructions should be followed: - Make sure to list all the investments approved by the EIB/Investment Committee until the cut-off date and include the subsequent disbursements in the separate dedicated column. - Please indicate in column J whether an investments was discontinued, partlially discontinued or modified. Subsequently, please adapt all the other inputs and especially the indicators covered by the 'Contribution to Green Deal Objectives'. For discontinued investments, the indicators (including budget) should be set to zero. - Location of the investment (for schemes, provide locations of all investments funded) - please provide the more precise location, not just the Member State. - Total confirmed/recommended support from the Modernisation Fund for the investment in EUR refers to the Modernisation Fund support covered by a Disbursement Decision, that EIB disbursed to the beneficiery MS by the cut-off date. - GHG emissions saved (expected cumulative amount by the end of the investment lifetime) - please make sure that the estimation refers to investment lifetime and not annual emissions saved, as you present with the MF applications. - Column Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - by 31 December of the year preceding report submission) should be calculated both at the level of total investment costs but also at the level of planned MF support. The calculation formulas should be shown in the cells. - Column Abatement costs in EUR/tCO2 (if applicable given the nature of the investment) - expected cumulative amount by the end of the investment lifetime, should be calculated both at the level of total investment costs but also at the level of planned MF support. The calculation formula should be shown in the cells.
CLIMA-MODFUND@ec.europa.eu
copying EIB (European Investment Bank):
Modernisation-fund@eib.org
Year of Annual Report: |  | Beneficary Member State (Dropdown Menu):
2025 | Poland | [6 empty] | should we already add the new bMS?
Share of priority investements compared to all investment | Article 10(1), third subparagraph – (2%) (min 80% priority investments) | Article 10(1), fourth subparagraph - (2.5%) (min 90% priority investments) | Article 10d(4) - (Transfers) (min 80% priority investment)
Ratios | 92.33% | 96.87% | #DIV/0!

## Annual Report
4.2806
General information | [13 empty] | Financial information | [12 empty] | Contribution to Green Deal Objectives | [10 empty] | Implementation
Number | Reference of the investment (as indicated in the applicable disbursement decision; for schemes, indicate the reference indicated in the first disbursement decision) | Reference of the subsequent disbursements (if any) | Name of the investment (as indicated in the relevant disbursement decision) | Priority or non-riority | Type of investment | Please indicate if the investment was discontinued; or if not whether the investment was modified compared to the initial application (czy została przerwana) | Implementation status (only for ongoing investments, even if partially discontinued or modified) status realizacji | Implementation modality (for all investments) rodzaj grantu | State aid regime (for all investments) pomoc publiczna | Link to national legal basis for the scheme (not applicable to projects) | Final beneficiary of the support (in case of schemes, please list the final beneficiaries that have been awarded support to date) | Type of end beneficiary | Location of the investment (for schemes, provide locations of all investments funded) | Total investment costs/total volume of the scheme/project with VAT in EUR | Total investment costs/total volume of the scheme/project without VAT in EUR | Total planned support from the Modernisation Fund for the investment in EUR | Total confirmed/recommended support from the Modernisation Fund for the investment in EUR |  |  | Total amount covered by a legal commitment between the beneficiary Member State/managing authority and the project proponent/final recipients of Modernisation Fund support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR |  | Total amount paid by the beneficiary Member State/scheme managing authority to the project proponent/final recipients of Modernisation support (cut-off date: 31 December of the year preceding report submission) (for schemes: aggregated figure) in EUR |  |  | Any amounts recovered by the beneficiary Member State from the project proponent or the scheme managing authority, and the dates of recovery, in EUR; date | Confirmation of co-financing from private sources (both for priority investments if applicable but especially for non-priority investments) in EUR - | An assessment of the added value of the investment in terms of energy efficiency and modernisation of the energy system, including information on the following (for schemes: aggregated figures). Please provide explanations where needed. | [10 empty] | Was the investment included in a preceding overview of planned investments in accordance with Article 13(2), and if so, which one. Format: [Yes/No, Year] | Milestones achieved since the previous annual report; (for schemes, this can include, for instance, information about calls for proposals, project selection, agreements concluded with the final recipients of Modernisation Fund support) | For investments other than schemes: expected entry into operation [Date: DD/MM/20YY] | Identified or expected delays in implementation | For investments other than schemes: identified or expected changes in eligible costs, technology applied or results of an investment | Description of and links to audits undertaken at national level in accordance with Article 16(4) of the Implementing Regulation 2020/1001 | For large-scale projects and large-scale schemes, when reporting on the project or scheme for the first time: overview of the consultation carried out. | Explanation of how the investment complies with the 'Do-no-significant-harm' criteria, in accordance with Article 10f of the Directive 2003/87/EC (only applicable for investments approved after 1 January 2025)
[12 empty] | Type of end beneficiary | [8 empty] | Date of the legal commitment [Date: DD/MM/20YY] |  | Date of the first payment [Date: DD/MM/20YY] | Date of the last payment [Date: DD/MM/20YY] |  |  | Energy saved in MWh |  |  | Greenhouse gas emissions saved in tCO2 |  | Additional renewable energy capacity installed, if applicable, in MW |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment), calculated as Total investment costs/total volume of the scheme/project with VAT over GHG emissions saved |  | Abatement costs in EUR/tCO2 (if applicable given the nature of the investment), calculated as Total planned support from the Modernisation Fund for the investment over GHG emissions saved
[17 empty] | Article 10(1), third subpara graph – (2%) | Article 10(1), fourth subparagraph - (2.5%) | Article 10d(4) - (Transfers) | [7 empty] | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | Relative energy savings - expected at the end of the investment lifetime (%) - if applicable | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime | by 31 December of the year preceding report submission | expected cumulative amount by the end of the investment lifetime
1 | MF 2021-1 PL 0-004 |  | Renovation with a guarantee of savings | Priority | Scheme | Unchanged compared to initial application | Ongoing: construction phase | Partial grants (less than 50%) of total invesments costs | No State aid | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Polczynskie Przedsiebiorstwo Komunalne sp. z o.o. - Gmina Łomianki - Gmina Miasto Szczecin - Gminia i Miasto Odolanów - Aqua Cedry Sp. z o.o. - Miasto Łódź | Podmioty mieszane lub publiczno-prywatne - odbiorcy energii - przemysł (Mix or public and private entities - energy consumers - industry) | Poland | 123000000 | 100000000 | 25000000 | 25000000 |  |  | 7883259.1226 | 2023-07-21 2025-04-30 2025-04-30 2025-04-29 2025-04-30 2025-04-30 | 527682.1006 | 2023-07-28 | 2023-12-05 | 0 | n/a | 5326 | 152778 | 3.486% | 1783 | 45000 | n/a | n/a | 68984.857 | 2733.3333 | 14021.3124 | 555.5556 | no | calls for proposals: 2 project proposals: 36 agreements concluded: 6 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
2 | MF 2021-1 PL 0-003 | MF 2022-2 PL 0-001 | Smart energy infrastructure | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | 100% grants | No State aid | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Stoen Operator; - Energa Operator; - PGE Dystrybucja; - TAURON Dystrybucja S.A.; - ENEA Operator Sp. z o.o. | Podmiot publiczny - dystrybucja i sieci (Public entity - distribution and networks) | Poland | 373920000 | 304000000 | 222000000 | 222000000 |  |  | 228021157.548 | 27.07.2023 04.09.2023 13.10.2023 10.07.2024 28.08.2024 09.09.2024 09.09.2024 09.12.2024 23.12.2025 19.12.2025 | 110068518.6656 | 2023-07-28 | 2025-12-12 | 330492.3936 | n/a | 513849.73 | n/a | n/a | 276124 | 362000 | n/a | n/a | 1354.1742 | 1032.9282 | 803.9866 | 613.2597 | no | calls for proposals: 3 project proposals: 12 agreements concluded: 11 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
3 | MF 2021-1 PL 0-006 | MF 2023-2 PL 0-003 | Development of the power grid for future electric car charging stations | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Partial grants (between 50% and 80%) of total investments costs | No State aid | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - ENEA Operator; - STOEN Operator; - ENERGA Operator; - PGE Dystrybucja; - TAURON Dystrybucja S.A. | Podmiot publiczny - dystrybucja i sieci (Public entity - distribution and networks) | Poland | 455100000 | 370000000 | 222000000 | 127000000 |  |  | 179557887.2121 | 29.12.2022 28.12.2022 29.03.2023 29.03.2023 01.06.2023 11.10.2023 28.11.2024 13.03.2025 01.04.2025 08.04.2025 30.07.2025 30.07.2025 29.10.2025 30.09.2025 | 73066920.7588 | 2023-07-26 | 2025-12-23 | 0 | n/a | n/a | n/a | n/a | 19071 | 3443 | n/a | n/a | 23863.4576 | 132181.2373 | 6659.3257 | 36886.4362 | no | calls for proposals: 4 project proposals: 352 agreements concluded: 14 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
4 | MF 2021-2 PL 0-002 | MF 2023-2 PL 0-002 | Cogeneration for Energy and Industry | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Velvet Care Sp.z o.o.; - QEMETICA Soda Polska Spółka Akcyjna | Podmiot prywatny - odbiorca energii - przemysł (Private entity - energy consumer - industry) | Poland | 546120000 | 444000000 | 444000000 | 69140000 |  |  | 30791161.2858 | 17.08.2023 08.10.2024 | 467224.2209 | 2023-11-30 | 2023-11-30 | 467224.2209 | n/a | 185987 | 2660000 | 6.992% | 287563 | 3192000 | n/a | n/s | 1899.1317 | 171.0902 | 240.4343 | 21.6604 | no | calls for proposals: 2 project proposals: 13 agreements concluded: 2 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
5 | MF 2023-2 PL 0-001 |  | Cogeneration for Energy and Industry - sectors in energy trasition | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Tartak Napiwoda Sp. z o.o. | Podmiot prywatny - odbiorca energii - przemysł (Private entity - energy consumer - industry) | Poland | 410820000 | 334000000 | 334000000 |  | 44570000 |  | 6261038.1722 | 01.09.2025 01.09.2025 | 0 | n/a | n/a | 0 | n/a | 15896 | 2006667 | 0.7922% | 12877 | 2408000 | n/a | n/a | 31903.3936 | 170.6063 | 3461.2099 | 18.5091 | no | calls for proposals: 1 project proposals: 142 agreements concluded: 2 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement
6 | MF 2021-2 PL 0-003 |  | Cogeneration For District heating | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Miejska Energetyka Cieplna w Koszalinie sp. z o.o.; - Miejskie Przedsiebiorstwo Energetyki Cieplnej sp. z o.o. | Podmiot publiczny - producent energii (Public entity - energy producer) | Poland | 819991800 | 666660000 | 666660000 | 66600000 |  |  | 37507337.2892 | 05.12.2023 08.12.2023 09.12.2023 29.12.2023 | 2336.1211 | 2023-12-08 | 2023-12-08 | 0 | n/a | 406703 | 4166667 | 9.761% | 66828 | 6000000 | n/a | n/a | 12270.1832 | 136.6653 | 996.5883 | 11.1 | no | calls for proposals: 2 project proposals: 69 agreements concluded: 4 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
7 | MF 2023-1 PL 0-002 | MF 2025-1 PL 0-002 | Cogeneration For District heating - part II | Priority | Scheme | Unchanged compared to initial application | Ongoing: tendering phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Przedsiebiorstwo Energetyki Cieplnej w Suwalkach sp. z o.o. | Podmiot publiczny - producent energii (Public entity - energy producer) | Poland | 27330600 | 22220000 | 22220000 | 20000000 | 2220000 |  | 24581829.65 | 29.12.2023 29.12.2023 | 19665463.72 | 2024-08-29 | 2025-12-16 | 3528968.745 | n/a | 77268 | 55556 | 139.1% | 39309 | 60000 | 7.35 | n/a | 695.2759 | 455.51 | 565.265 | 370.3333 | no | calls for proposals: 1 project proposals: 8 agreements concluded: 2 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
8 | MF 2021-2 PL 0-005 |  | Digitisation of heating networks | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Okręgowe Przedsiębiorstwo Energetyki Cieplnej Sp. z. o. o. w Puławach - Przedsiębiorstwo Energetyki Cieplnej Sp. z o.o. w Bełchatowie - Przedsiębiorstwo Energetyki Cieplnej "PEC" Sp. z o.o. (Kwidzyn) - Veolia Energia Warszawa S.A. - Lubelskie Przedsiębiorstwo Energetyki Cieplnej S.A. - U&R CALOR Sp. z o.o. - CALOR Energetyka Cieplna Sp. z o.o. - Przedsiębiorstwo Energetyki Cieplnej - GLIWICE sp. z o. o. - Przedsiębiorstwo Energetyki Cieplnej w Gnieźnie Sp. z o.o. - U&R CALOR Sp. z o.o. - Elektrociepłownia Ciechanów Sp. z o. o. - Veolia Energia Poznań S.A. - Miejska Gospodarka Komunalna Sp. z o. o. - Szczecińska Energetyka Cieplna Spółka z ograniczoną odpowiedzialnością - Przedsiębiorstwo Energetyki Cieplnej w Gnieźnie Sp. z o. o. - Gdańskie Przedsiębiorstwo Energetyki Cieplnej Sp. z o. o. SEC Zgorzelec Sp. z o.o. - Przedsiębiorstwo Energetyki Cieplnej w Ełku Sp. z o.o. - Przedsiębiorstwo Energetyczne w Siedlcach Sp. z o.o. - Przedsiębiorstwo Energetyki Cieplnej Sp. z o.o. w Hajnówce - Fortum Power and Heat Polska Sp. z o.o. - Miejskie Przedsiębiorstwo Energetyki Cieplnej Sp. z o.o. - Miejskie Sieci Cieplne w Zduńskiej Woli Sp. z o.o. - Miejskie Przedsiębiorstwo Energetyki Cieplnej Sp. z o.o. w Nowym Sączu - U&R CALOR Sp. z o.o. - SEC Chojnice Sp. z o.o. - Miejskie Przedsiębiorstwo Energetyki Cieplnej Sp. z o. o. w Ostródzie - Zakład Usług Technicznych Sp. z o.o. - Miejskie Przedsiębiorstwo Energetyki Cieplnej Sp. z o. o. w Ostródzie | Podmiot publiczny - producent energii (Public entity - energy producer) | Poland | 136665300 | 111110000 | 111110000 | 33300000 |  |  | 44339928.9819 | from 22.11.2023 to 30.12.2025 | 8571250.9929 | 2023-12-06 | 2025-11-28 | 1496004.1443 | n/a | 124084 | 83333 | 148.9% | 37123 | 37000 | n/a | n/a | 3681.4185 | 3693.6568 | 897.018 | 900 | no | calls for proposals: 3 project proposals: 104 agreements concluded: 49 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
9 | MF 2021-2 PL 0-004 | MF 2022-1 PL 0-001 | The use of alternative fuels for energy purposes | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: https://www.gov.pl/web/funduszmodernizacyjny/zawarte-umowy | Podmiot prywatny - producent energii (Private entity - energy producer) | Poland | 273060000 | 222000000 | 222000000 | 222000000 | 400000000 |  | 108676261.5054 | 19.12.2022 21.12.2022 19.12.2022 | 5770011.2134 | 2023-12-06 | 2023-12-06 | 134759.69 | n/a | 32510 | n/a | n/a | 6694 | 151295 | n/a | n/a | 40791.7538 | 1804.8184 | 92919.032 | 4111.1735 | no | calls for proposals: 1 project proposals: 20 agreements concluded: 6 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
10 | MF 2022-1 PL 0-007 | MF 2024-1 PL 0-003 | The use of alternative fuels for energy purposes | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: https://www.gov.pl/web/funduszmodernizacyjny/zawarte-umowy | Podmiot prywatny - producent energii (Private entity - energy producer) | Poland | 655590000 | 533000000 | 444000000 | 44400000 | 399600000 |  | 462049876.1856 | from 23.03.2023 to 14.12.2023 | 59191906.5084 | 2023-12-01 | 2023-12-01 | 0 | n/a | 171751 | n/a | n/a | 284049 | 5680980 | n/a | n/a | 2308.0173 | 115.4009 | 1563.1106 | 78.1555 | no | calls for proposals: 1 project proposals: 48 agreements concluded: 18 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
11 | MF 2023-1 PL 0-001 | MF 2024-1 PL 0-002 and MF 2024-2 PL 0-010 | The use of alternative fuels for energy purposes | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: https://www.gov.pl/web/funduszmodernizacyjny/zawarte-umowy | Podmiot prywatny - producent energii (Private entity - energy producer) | Poland | 933000000 | 755000000 | 666000000 |  | 222400000 |  | 116637772.9758 | 27/12/2023 17.07.2024 25.11.2025 | 13873989.6276 | 2025-09-25 | 2025-09-25 | 0 | n/a | 54562 | n/a | n/a | 50739 | 1197362 | n/a | n/a | 18388.2221 | 779.213 | 4383.2161 | 185.7417 | no | calls for proposals: 1 project proposals: 52 agreements concluded: 6 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
12 | MF 2021-2 PL 0-001 |  | Support for the use of storages and other devices for network stabilization - a scheme for DSOs | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Partial grants (between 50% and 80%) of total investments costs | No State aid | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - PGE Dystrybucja - Stoen Operator Sp. z o.o. -Tauron Dystrybucja S.A. - Enea Operator Sp.z o. o. | Podmiot publiczny - dystrybucja i sieci (Public entity - distribution and networks) | Poland | 492000000 | 400000000 | 222220000 | 44440000 |  |  | 19897444.2835 | 07.12.2023 27.11.2024 22.04.2025 15.05.2025 | 65598.2806 | 2023-12-13 | 2024-11-26 | 0 | n/a | n/a | n/a | n/a | 2520 | 50400 | n/a | n/a | 195238.0952 | 9761.9048 | 17634.9206 | 881.746 | no | calls for proposals: 2 project proposals: 9 agreements concluded: 4 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
13 | MF 2022-1 PL 0-004 | MF 2024-2 PL 0-009 | Energy-intensive Industry – RES | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | Financial instruments - loans | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Enea Ciepło Spółka z ograniczoną odpowiedzialnością; - Elektrociepłownia "Zielona Góra" Spółka Akcyjna - PGE Energia Ciepła Spółka Akcyjna | Podmiot publiczny - producent energii (Public entity - energy producer) | Poland | 212790000 | 173000000 | 144000000 |  | 21110000 |  | 15180488.7165 | 17.02.2024 14.11.2024 26.03.2025 | 865089.7071 | 2025-06-11 | 2025-06-11 | 0 | n/a | n/a | 130000 | n/a | 2424 | 95000 | 3.83 | 85 | 87784.6535 | 2239.8947 | 8708.7459 | 222.2105 | no | calls for proposals: 2 project proposals: 7 agreements concluded: 3 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
14 | MF 2022-1 PL 0-003 | MF 2024-2 PL 0-008 | Energy-intensive industry - improving energy efficiency | Priority | Scheme | Unchanged compared to initial application | Ongoing: tendering phase | Financial instruments - loans | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Südzucker Polska Spółka Akcyjna | Podmiot prywatny - odbiorca energii - przemysł (Private entity - energy consumer - industry) | Poland | 114820500 | 93350000 | 77790000 | 11110000 | 50000000 |  | 29902350.1378 | 2023-12-12 | 299023.5014 | 2024-07-10 | 2024-07-10 | 0 | n/a | n/a | n/a | n/a | 30157 | 80000 | n/a | n/a | 3807.4245 | 1435.2562 | 2026.3952 | 763.875 | no | calls for proposals: 2 project proposals: 1 agreements concluded: 1 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
15 | MF 2022-2 PL 0-003 | MF 2024-1 PL 0-001 | Energy for Rural Areas | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: https://www.gov.pl/web/funduszmodernizacyjny/zawarte-umowy | Podmiot prywatny - producent energii (Private entity - energy producer) | Poland | 258200000 | 209918699.187 | 209900000 | 20990000 | 66660000 |  | 128178666.7757 | from 30.06.2023 to 31.12.2025 | 82294379.7598 | 2023-08-21 | 2025-11-06 | 1441591.7185 | n/a | n/a | n/a | n/a | 66391 | 195311 | 4 | 30 | 3889.0814 | 1321.9942 | 1320.2091 | 448.7714 | no | calls for proposals: 1 project proposals: - agreements concluded: 126 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
16 | MF 2022-2 PL 0-002 |  | Cogeneration for counties | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Sanockie Przedsiębiorstwo Gospodarki Komunalnej Sp. z o.o. - Celsium serwis Sp. z o.o. - Veolia Północ Sp. z o.o. | Podmiot publiczny - producent energii (Public entity - energy producer) | Poland | 273330600 | 222220000 | 222220000 | 22200000 |  |  | 9010386.3944 | 30.12.2024 30.12.2025 06.05.2025 08.12.2025 | 2785731.2059 | 2025-07-24 | 2025-12-29 | 0 | n/a | 12505 | 555556 | 2.251% | 52615 | 600000 | n/a | n/a | 5194.9178 | 455.551 | 421.9329 | 37 | no | calls for proposals: 2 project proposals: 108 agreements concluded: 4 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
17 | MF 2022-2 PL 0-004 | MF 2024-2 PL 0-007 | Development of cogeneration based on municipal biogas | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Miedzygminny Kompleks Unieszkodliwiania Odpadow ProNatura sp. z o.o. - EKO DOLINA Spółka Z o.o - Centrum Zielonej Energii Subregionu Zachodniego w Rybniku - Przedsiębiorstwo Usługowe Hetman Sp. z o.o. | Podmiot prywatny - producent energii (Private entity - energy producer) | Poland | 409590000 | 333000000 | 333000000 | 44440000 | 260000000 |  | 84646271.7843 | 28.12.2023 28.12.2023 23.10.2025 23.10.2025 16.12.2025 16.12.2025 | 3869177.2181 | 2025-12-16 | 2025-12-29 | 0 | n/a | 23326 | 502238 | 4.644% | 31852 | 690710 | 6 | 15 | 12859.1611 | 592.9985 | 9557.9555 | 440.7639 | no | calls for proposals: 1 project proposals: 55 agreements concluded: 8 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
18 | MF 2022-2 PL 1-001 | MF 2025-2 PL 0-001 | RES - heat sources for district heating | Non-priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: - Przedsiębiorstwo Energetyki Cieplnej - Gliwice Sp. z o.o. - Miejskie Przedsiębiorstwo Infrastruktury "KOS-EKO" Sp. z o.o - Dalkia Polska Energia S.A. | Podmiot publiczny - producent energii (Public entity - energy producer) | Poland | 780952381.05 | 634920635 | 444444444 | 22222222 | 49000000 |  | 30569750.2687 | 25.04.2024 17.05.2024 30.12.2025 30.12.2025 30.12.2025 | 2626970.7518 | 2025-01-16 | 2025-01-22 | 0 | YES (applicant's statement and documents confirming payments) | 100581 | 1358789 | 7.402% | 32525 | 387062 | 29.46 | 898 | 24010.8342 | 2017.6416 | 2189.7685 | 184.0073 | no | calls for proposals: 1 project proposals: 70 agreements concluded: 5 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
19 | MF 2021-2 PL 1-001 | MF 2022-2 PL 1-002 | My Heating | Non-priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Partial grants (less than 50%) of total invesments costs | No State aid | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | The final recipients of the aid will be natural persons. The program is addressed to owners or co-owners (end recipients) of new single-family buildings. Beneficiaries that have been awarded support: https://mojecieplo.gov.pl/wyniki-naboru/ | Podmiot prywatny - odbiorca energii - budynki (Private entity - energy consumer - buildings) | Poland | 546612000 | 444400000 | 133300000 | 133333333 |  |  | 74513861.3068 | from 2022 to 2025 | 74513861.3068 | from 2022 to 2025 | from 2022 to 2025 | 8872.5179 | YES (applicant's statement and documents confirming payments) | 401511 | 625000 | 64.24% | 42353 | 65000 | 302.78 | 450 | 12906.0987 | 8409.4154 | 3148.1438 | 2051.282 | no | calls for proposals: 1 project proposals: 12954 agreements concluded: 36658 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | not applicable
20 | MF 2024-1 PL 0-005 |  | Support for the construction or expansion of a publicly accessible charging station for heavy transport | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | 100% grants | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Beneficiaries of the programme: entrepreneurs within the meaning of the Act of 6 March 2018 – Entrepreneurs' Law, who have their registered office or branch in the territory of the Republic of Poland. | Inne (Other) | Poland | 546612000 | 444400000 | 444400000 |  | 44400000 |  | 0 | n/a | 0 | n/a | n/a | 0 | n/a | n/a | n/a | n/a | 0 | 627000 | n/a | n/a | #DIV/0! | 871.7895 | #DIV/0! | 70.8134 | no | calls for proposals: 1 project proposals: 352 agreements concluded: - | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement
21 | MF 2024-1 PL 0-007 |  | My Wind Electric System | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Partial grants (less than 50%) of total invesments costs | No State aid | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | List of concluded contracts (Final Beneficiaries): https://www.gov.pl/web/funduszmodernizacyjny/zawarte-umowy | Podmiot prywatny - producent energii (Private entity - energy producer) | Poland | 200000000 | 162601626.0163 | 88890000 |  | 8880000 |  | 8807272.345 | from 2024 to 2025 | 8807272.345 | from 2024 to 2025 | from 2024 to 2025 | 102088.4923 | n/a | 10260 | 478000 | 2.146% | 2811 | 13100 | 4.1 | 19 | 71149.0573 | 15267.1756 | 3159.0181 | 677.8626 | no | calls for proposals: 1 project proposals: 2794 agreements concluded: 1269 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement
22 | MF 2024-2 PL 0-003 |  | Energy for Rural Areas | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: construction phase | Combination between grants and financial instruments | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Final beneficiaries up to date: https://www.gov.pl/web/funduszmodernizacyjny/zawarte-umowy | Podmiot prywatny - producent energii (Private entity - energy producer) | Poland | 592770000 | 481930000 | 481930000 |  | 24100000 |  | 0 | n/a | 0 | n/a | n/a | 0 | n/a | n/a | n/a | n/a | 0 | 484689 | 0 | 75.2 | #DIV/0! | 1222.9904 | #DIV/0! | 49.7226 | no | calls for proposals: 1 project proposals: 248 agreements concluded: - | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement
23 | MF 2024-2 PL 0-002 |  | Electricity storage facilities and related infrastructure to improve the stability of the Polish electricity grid. | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | Combination between grants and financial instruments | TCTF | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Beneficiaries of the programme: entrepreneurs within the meaning of the Act of 6 March 2018 – Entrepreneurs' Law, | Podmiot prywatny - odbiorca energii - inne (Private entity - energy consumer - other) | Poland | 1230000000 | 1000000000 | 1000000000 |  | 120500000 |  | 968178395.3184 | 30.12.2025 31.12.2025 | 0 | n/a | n/a | 0 | n/a | 0 | 1642500 | 0% | 1241730 | 1125113 | n/a | n/a | 990.5535 | 1093.2235 | 97.042 | 107.1004 | no | calls for proposals: 1 project proposals: 634 agreements concluded: 180 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement
24 | MF 2024-2 PL 0-001 |  | Construction/expansion of power grids for the needs of publicly available high-power charging stations | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | 100% grants | No State aid | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Beneficiaries of the programme: distribution system operators (DSOs) – electricity distribution system operators within the meaning of Article 3(25) of the Act of 10 April 1997 – Energy Law | Podmiot publiczny - dystrybucja i sieci (Public entity - distribution and networks) | Poland | 592773900 | 481930000 | 481930000 |  | 120500000 |  | 0 | n/a | 0 | n/a | n/a | 0 | n/a | n/a | n/a | n/a | 0 | 3190 | n/a | n/a | #DIV/0! | 185822.5392 | #DIV/0! | 37774.2947 | no | calls for proposals: 1 project proposals: 6 agreements concluded: - | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement
25 | MF 2024-2 PL 0-005 |  | Support for the purchase or leasing of zero-emission vehicles of N2 and N3 categories | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | Partial grants (less than 50%) of total invesments costs | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Beneficiaries of the programme: entrepreneurs within the meaning of the Act of 6 March 2018 – Entrepreneurs' Law, who have their registered office or branch in the territory of the Republic of Poland. | Inne (Other) | Poland | 1968000000 | 1600000000 | 481930000 |  | 50000000 |  | 0 | n/a | 0 | n/a | n/a | 0 | n/a | n/a | n/a | n/a | 0 | 73394 | n/a | n/a | #DIV/0! | 26814.181 | #DIV/0! | 681.2546 | no | calls for proposals: 1 project proposals: 53 agreements concluded: - | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement
26 | MF 2025-1 PL 0-001 |  | Clear Air | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: tendering phase | Partial grants (between 50% and 80%) of total investments costs | No State aid | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | The beneficiaries of the CAS are individuals (natural persons) who are owners/co-owners of single-family buildings/separate residential premises in single-family buildings. Under the scheme the division into three groups of beneficiaries exists and the amount of support they are entitled to depends on the income of the beneficiary or income per member of the beneficiary's household. The highest support is granted to the group at greatest risk of energy poverty, which is directly in line with art. 10d (2) of the ETS Directive ("support for low-income households to address energy poverty and to renovate their heating systems"). https://www.gov.pl/web/funduszmodernizacyjny/zawarte-umowy | Podmiot prywatny - odbiorca energii - budynki (Private entity - energy consumer - buildings) | Poland | 5248000000.41 | 4266666667 | 2470000000 | 900000000 | 400000000 |  | 466507348.9698 | from 2025 | 31210197.4022 | from 2025 | from 2025 | 19063.6943 | n/a | 1192264 | 2878590 | 41.42% | 661831 | 910417 | n/a | n/a | 7929.5168 | 5764.3915 | 1964.2477 | 1427.9171 | yes; 2024 | calls for proposals: 1 project proposals: 49811 agreements concluded: 32430 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | https://www.gov.pl/web/funduszmodernizacyjny/konsultacje-spoleczne-dotyczace-nowych-obszarow-wsparcia-z-funduszu-modernizacyjnego-na-lata-2024-2025-z-perspektywa-do-2030-r | call for proposals/ application selection criteria / beneficiary statement
27 | MF 2025-1 PL 0-003 |  | High efficiency biogas cogeneration from biomass, including municipal waste | Priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: confirmed but not started | Partial grants (less than 50%) of total invesments costs | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | The beneficiaries of the “High efficiency biogas cogeneration from biomass, including municipal waste” scheme are entrepreneurs within the meaning of the Act of 6 March 2018 on Entrepreneurs carrying out economic activities (Journal of Laws of 2024, item 236), with the exception of the beneficiaries specified in point 7.4. of the "Energy for Rural Areas" scheme*: | Podmiot prywatny - producent energii (Private entity - energy producer) | Poland | 382800000 | 311200000 | 247000000 |  | 12000000 |  | 0 | n/a | 0 | n/a | n/a | 0 | n/a | n/a | n/a | n/a | 0 | 107581 | 0 | 32 | #DIV/0! | 3558.2491 | #DIV/0! | 111.5439 | no | calls for proposals: in progress project proposals: - agreements concluded: - | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement
28 | MF 2025-2 PL 0-001 |  | Smart Energy Infrastructure 2.0 | Priority | Scheme | Unchanged compared to initial application | Ongoing: construction phase | 100% grants | No State aid | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Electricity Distribution System Operators (DSO) | Podmiot prywatny - dystrybucja i sieci (Private entity - distribution and networks) | Poland | 30750000 | 25000000 | 25000000 |  | 24600000 |  | 0 | n/a | 0 | n/a | n/a | 0 | n/a | 0 | 107864 | 0% | 0 | 32704 | n/a | n/a | #DIV/0! | 940.252 | #DIV/0! | 752.2016 | yes; 2025 | calls for proposals: 3 project proposals: 2 agreements concluded: 0 | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | https://www.gov.pl/web/funduszmodernizacyjny/konsultacje-spoleczne-dotyczace-nowych-obszarow-wsparcia-z-funduszu-modernizacyjnego-na-lata-2025-2026-z-perspektywa-do-2030-r | call for proposals/ application selection criteria / beneficiary statement
29 | MF 2025-2 PL 0-003 |  | Energy-intensive Industry 2.0 – improving energy efficiency | Priority | Scheme | Unchanged compared to initial application | Ongoing: construction phase | Financial instruments - loans | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | The scheme in question is dedicated to enterprises within the meaning of the Act of 6 March 2018 Entrepreneurs' Law having legal title to an installation covered by the greenhouse gas emission allowance trading scheme within the meaning of the Act of June 12, 2015 on the greenhouse gas emission allowance trading scheme, resulting from the ownership right, perpetual usufruct right or permanent management, which has not been liquidated or not bankruptcy proceedings are pending against. |  | Poland | 212870000 | 173065040.6504 | 119750000 |  | 10000000 |  | 0 | n/a | 0 | n/a | n/a | 0 | n/a | 0 | 259441 | 0% | 0 | 113039 | n/a | n/a | #DIV/0! | 1883.1554 | #DIV/0! | 88.465 | no | calls for proposals: 1 project proposals: 4 agreements concluded: - | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement
30 | MF 2025-2 PL 1-002 |  | Improvement of energy security through the use of biomethane | Non-priority | Large-scale scheme | Unchanged compared to initial application | Ongoing: confirmed but not started | Partial grants (less than 50%) of total invesments costs | GBER | https://www.gov.pl/web/funduszmodernizacyjny/podstawy-prawne Program Priorytetowe w ramach środków z Funduszu Modernizacyjnego - Fundusz Modernizacyjny - Portal Gov.pl (www.gov.pl) | Beneficiaries of the programme: entrepreneurs within the meaning of the Act of 6 March 2018 – Entrepreneurs' Law |  | Poland | 663000000 | 539024390.2439 | 198000000 |  | 24800000 |  | 0 | n/a | 0 | n/a | n/a | 0 | YES (applicant's statement and documents confirming payments) | n/a | n/a | n/a | 0 | 36500 | n/a | n/a | #DIV/0! | 18164.3836 | #DIV/0! | 679.4521 | no | calls for proposals: in progress project proposals: - agreements concluded: - | not applicable (only scheme) | No delays Extend call for proposals Extendet contracting phase. | not applicable (only scheme) | Audit not yet conducted/audit pending | not applicable | call for proposals/ application selection criteria / beneficiary statement

## Overview Planned Investments
|  | 1. Overview of investments planned in the next two calendar years and, where possible, the outlook until 2030 | [7 empty] | 2. Information about the outcome of stakeholder consultation on the draft overview of investments under Article 13(5)
Number | Name and reference of the investment | 1.1. Name of the project proponent or the scheme managing authority | 1.2. Specific location of the investment or the geographical scope of the scheme (location name, country name) | 1.3. Estimate of the total cost of the investment |  | 1.5. Status of any State aid assessment concerning the investment, where applicable (completed, pending,not applicable) | 1.6. Estimate of the financing from the Modernisation Fund and outline of the intended financing proposals | 1.7. Information on the relation between the investment and the integrated National Energy and Climate Plan (NECP), in particular with regard to the national objectives, targets, policies and measures and the investment needed. | 1.8. Information on whether the investment has been awarded a seal or any quality label foreseen by the Union law after having been evaluated positively in a directly managed funding programmes | 2.1 Dates of consultation | 2.1 Format of consultation | 2.1 Types of stakeholders consulted | 2.1 Number of replies received | 2.1. Summary of the replies
1.4 Summary description of the investment
1
2
3
4
5
6
7
8
9
10
11
XX

## Dropdown Menu
bMS | Year
Column1 | Column2
- | 2021 | Priority | Ongoing: confirmed but not started | Fully discontinued | 100% grants | GBER | Public entity - energy consumer - industry | Podmiot publiczny - odbiorca energii - przemysł | Podmiot publiczny - odbiorca energii - przemysł (Public entity - energy consumer - industry)
Bulgaria | 2022 | Non-priority | Ongoing: tendering phase | Partially discontinued | Partial grants (between 50% and 80%) of total investments costs | CEEAG | Public entity - energy consumer - services | Podmiot publiczny - odbiorca energii - usługi | Podmiot publiczny - odbiorca energii - usługi (Public entity - energy consumer - services)
Czechia | 2023 |  | Ongoing: construction phase | Modified | Partial grants (less than 50%) of total invesments costs | CISAF | Public entity - energy consumer - buildings | Podmiot publiczny - odbiorca energii - budynki | Podmiot publiczny - odbiorca energii - budynki (Public entity - energy consumer - buildings)
Estonia | 2024 |  | Completed (for schemes) | Unchanged compared to initial application | Financial instruments - loans | TCTF | Public entity - energy consumer - other | Podmiot publiczny - odbiorca energii - inne | Podmiot publiczny - odbiorca energii - inne (Public entity - energy consumer - other)
Greece | 2025 |  | Entered into operation (for investments other than schemes) |  | Financial instruments - equity | No State aid | Public entity - energy producer | Podmiot publiczny - producent energii | Podmiot publiczny - producent energii (Public entity - energy producer)
Croatia | 2026 |  | Not applicable (investment fully discontinued) |  | Financial instruments - financial guarantees | De minimis | Public entity - distribution and networks | Podmiot publiczny - dystrybucja i sieci | Podmiot publiczny - dystrybucja i sieci (Public entity - distribution and networks)
Latvia | 2027 |  |  |  | Combination between grants and financial instruments | Other | Private entity - energy consumer - industry | Podmiot prywatny - odbiorca energii - przemysł | Podmiot prywatny - odbiorca energii - przemysł (Private entity - energy consumer - industry)
Lithuania | 2028 |  |  |  | Other |  | Private entity - energy consumer - services | Podmiot prywatny - odbiorca energii - usługi | Podmiot prywatny - odbiorca energii - usługi (Private entity - energy consumer - services)
Hungary | 2029 |  | W toku: potwierdzono, ale nie rozpoczęto |  |  |  | Private entity - energy consumer - buildings | Podmiot prywatny - odbiorca energii - budynki | Podmiot prywatny - odbiorca energii - budynki (Private entity - energy consumer - buildings)
Poland | 2030 |  | W toku: faza przetargowa |  |  |  | Private entity - energy consumer - other | Podmiot prywatny - odbiorca energii - inne | Podmiot prywatny - odbiorca energii - inne (Private entity - energy consumer - other)
Portugal |  |  | W toku: faza budowy |  |  |  | Private entity - energy producer | Podmiot prywatny - producent energii | Podmiot prywatny - producent energii (Private entity - energy producer)
Romania |  |  | Zakończono (dla projektów) |  |  |  | Private entity - distribution and networks | Podmiot prywatny - dystrybucja i sieci | Podmiot prywatny - dystrybucja i sieci (Private entity - distribution and networks)
Slovenia |  |  | Oddano do eksploatacji (dla inwestycji innych niż projekty) |  |  |  | Public-private partnerships - energy consumer - industry | Partnerstwa publiczno-prywatne - odbiorca energii - przemysł | Partnerstwa publiczno-prywatne - odbiorca energii - przemysł (Public-private partnerships - energy consumer - industry)
Slovakia |  |  | Nie dotyczy (inwestycja całkowicie wstrzymana) |  |  |  | Public-private partnerships - energy consumer - buildings or residential | Partnerstwa publiczno-prywatne - odbiorca energii - budynki lub budynki mieszkalne | Partnerstwa publiczno-prywatne - odbiorca energii - budynki lub budynki mieszkalne (Public-private partnerships - energy consumer - buildings or residential)
[7 empty] | Public-private partnerships - energy consumer - services | Partnerstwa publiczno-prywatne - odbiorca energii - usługi | Partnerstwa publiczno-prywatne - odbiorca energii - usługi (Public-private partnerships - energy consumer - services)
[7 empty] | Public-private partnerships - energy consumer - other | Partnerstwa publiczno-prywatne - odbiorca energii - inne | Partnerstwa publiczno-prywatne - odbiorca energii - inne (Public-private partnerships - energy consumer - other)
[7 empty] | Public-private partnerships - energy producer | Partnerstwa publiczno-prywatne - producent energii | Partnerstwa publiczno-prywatne - producent energii (Public-private partnerships - energy producer)
[7 empty] | Public-private partnerships - distribution and networks | Partnerstwa publiczno-prywatne - dystrybucja i sieci | Partnerstwa publiczno-prywatne - dystrybucja i sieci (Public-private partnerships - distribution and networks)
[7 empty] | Mix or public and private entities - energy consumers - industry | Podmioty mieszane lub publiczno-prywatne - odbiorcy energii - przemysł | Podmioty mieszane lub publiczno-prywatne - odbiorcy energii - przemysł (Mix or public and private entities - energy consumers - industry)
[7 empty] | Mix or public and private entities - energy consumers - services | Podmioty mieszane lub publiczno-prywatne - odbiorcy energii - usługi | Podmioty mieszane lub publiczno-prywatne - odbiorcy energii - usługi (Mix or public and private entities - energy consumers - services)
[7 empty] | Mix or public and private entities - energy consumers - buildings | Podmioty mieszane lub publiczno-prywatne - odbiorcy energii - budynki | Podmioty mieszane lub publiczno-prywatne - odbiorcy energii - budynki (Mix or public and private entities - energy consumers - buildings)
[7 empty] | Mix or public and private entities - energy consumers - other | Podmioty mieszane lub Podmioty publiczne i prywatne – odbiorcy energii – inne | Podmioty mieszane lub Podmioty publiczne i prywatne – odbiorcy energii – inne (Mix or public and private entities - energy consumers - other)
[7 empty] | Mix or public and private entities - energy producers | Podmioty mieszane – producenci energii | Podmioty mieszane – producenci energii (Mix or public and private entities - energy producers)
[7 empty] | Mix or public and private entities - distribution and networks | Podmioty mieszane – dystrybucja i sieci | Podmioty mieszane – dystrybucja i sieci (Mix or public and private entities - distribution and networks)
[7 empty] | Other | Inne | Inne (Other)